## Blatt1 (2)
hoccer Release Timeline for forced and syncronized releases | [6 empty] | draft
Swimming Lanes
|  | PO | Q&A | Backend | Android | iOS | external
Update begin
|  | update Release notes & App Store Screenshots in Git | update Release notes & App Store Screenshots in Git
Setup & deploy review server (only used for iOS review process)
ngnix: map client to review server
finished Q&A for iOS
| ~7 d |  |  |  |  | submit iOS client to review (+screenshots +text)
iOS client is approved by review
ngnix: map to production server
finished Q&A for Android
Build APK + put on GitHub + Email Release Checklist (signed)
Client DB Migration Test
~3 h | 2-3 h |  |  |  | submit + release Android client (+screenshots +texts) | release iOS client
Android client available in store
iOS client available in store
~15 min |  |  |  | Server switch off
DB dump
| ~10 min |  |  | Server restart and deploy server update
migration of db
|  |  | Inform Beta Testers on release |  |  | Release Version to Testser
Update finished

## Blatt1
Task | Android | iOS | Server | Responsibility
update Release notes & App Store Screenshots in Git | x | x |  | PO / Q&A
Setup & deploy review server (only used for iOS review process) |  |  | x | AM
ngnix: map client to review server |  |  | x | AM
finished Q&A for iOS |  | x |  | Q&A
submit iOS client to review (+screenshots +text) |  | x |  | PM
iOS client is approved by review |  | x |  | Apple
ngnix: map to production server |  |  | x | AM
finished Q&A for Android | x |  |  | Q&A
Build APK + put on GitHub | x |  |  | Cologne
submit + release Android client (+screenshots +texts) | x |  |  | Cologne
release iOS client |  | x |  | PM / Cologne
Android client available | x |  |  | Google store
iOS client available |  | x |  | Apple store
deploy server update |  |  | x | AM
migration of db |  |  | x | AM
PO: Product Owner
Q&A: Quality Testing
AM: Andreas Marr
PM: Pavel Mayer
2-3h
3+h
~10min
~7d